FEASIBILITY REPORT

PEGS: Progressive Evidence-Governed Selection

A Two-Stage, Computationally Governed Architecture for Evidence-Based Resume Screening

Version 2.0 — Revised for Two-Stage Adaptive Architecture

(Supersedes v1.0 — single-pass pipeline design)

| Student Name | [FILL IN] |
| --- | --- |
| Roll Number | [FILL IN] |
| Program | B.Tech, Computer Science & Engineering |
| Project Category | Final-Year Minor Project — Research Paper Track |
| Supervisor / Advisor | [FILL IN] |
| Report Version | 2.0 (Two-Stage Architecture) |
| Project Start Date | [FILL IN] |
| Planned Duration | 10 weeks (~2.5 months) |

# 1. What Changed From v1.0

This revision replaces the single-pass screening design with a two-stage architecture: a cheap preliminary screening funnel (Stage 1) feeding a smaller, expensive evidence-governed assessment (Stage 2 / GADS), connected by an Adaptive Gate. The change was adopted after a structured review of an external architectural proposal; the table below records exactly what was accepted, simplified, or deferred, so the team never builds against an ambiguous specification.

| Decision | Disposition |
| --- | --- |
| Two-stage architecture (cheap screen → expensive governed assessment) | ADOPTED — becomes the project's core design |
| K′ buffer: send more candidates to Stage 2 than the final shortlist size K, to absorb hard-constraint failures | ADOPTED — fixed multiplier, e.g. K′ = 2–3 × K |
| Adaptive Gate using three signals (volume, role complexity, score distribution) | SIMPLIFIED — score-distribution signal only for this project |
| Progressive expansion of the Stage-2 pool with two stopping conditions (quantity threshold + shortlist-stability threshold) | ADOPTED — fixed batch sizes, both stopping conditions implemented |
| Exhaustion condition: if the whole pool is examined and still short, report insufficiency rather than lowering the bar | ADOPTED, plus one addition: log which mandatory (hard) requirement caused the most failures |
| Experiment: vary Stage-1 depth (5–25% of pool) and measure recall / cost / stability | ADDED as optional Experiment 5 — only if E1–E4 finish early |
| Full adaptive batch sizing driven by prior-batch yield | DEFERRED to future work |
| Role Assessment Complexity Score (six sub-components) | DEFERRED to future work |
| Boundary-exploration mechanism (anomaly detection to recover Stage-1 mistakes) | DEFERRED to future work |

# 2. Project Definition

## 2.1 Research Question (Upgraded)

“Can an adaptive two-stage screening architecture minimize expensive evidence-governed evaluation while maintaining a predefined level of candidate coverage and shortlist stability?”

This supersedes the v1.0 question (“Does evidence-governed screening improve resume evaluation?”). The new framing carries two distinct, separately measurable contributions:

- Evidence Governance — OPA policy-based candidate evaluation, with a full auditable evidence trail, replacing opaque scoring.

- Computational Governance — an adaptive gate that decides how much expensive evaluation is actually necessary, instead of running the expensive path on every candidate.

## 2.2 Pipeline Summary

Resume → Stage 1 (Preliminary Screening) → Adaptive Gate → Stage 2 / GADS (Governed Assessment) → Progressive Expansion Loop → Final Shortlist + Audit Trail.

- Stage 1 — Preliminary Screening: extraction, skill normalization, semantic matching. Cheap, runs on the full applicant pool.

- Adaptive Gate: examines the Stage-1 score distribution to select a pool of size K′ (K′ > K, the target shortlist size) to send forward. Score-distribution-only for this project.

- Stage 2 / GADS: OPA policy checks (hard and soft constraints), evidence ledger construction, uncertainty computation, human-review routing for uncertain cases.

- Progressive Expansion: if Stage 2 yields fewer than K qualified candidates after examining K′, pull the next fixed-size batch from Stage 1's ranking and repeat, until either the quantity threshold is met or the shortlist stabilizes (Jaccard / boundary-delta below threshold) across two consecutive batches.

- Exhaustion Condition: if the entire pool is exhausted and qualified count is still below the target, the system reports insufficiency explicitly — rather than relaxing hard constraints — and logs which mandatory requirement filtered the most candidates.

# 3. Scope Boundaries

Every component of the revised architecture, classified so nobody starts building something that was deliberately deferred.

| Component | Status | Reason |
| --- | --- | --- |
| Stage 1 screening (extraction, skill normalization, semantic matching) | IN SCOPE | Reuses/extends the existing pipeline; foundation for everything downstream. |
| K′ buffer sizing (fixed multiplier over target shortlist size) | IN SCOPE | Simple, directly solves the top-K gap problem from hard-constraint failures. |
| Adaptive Gate — score-distribution signal only (percentile / natural-gap detection) | SIMPLIFIED | Keeps real adaptivity without a multi-week calibration effort. |
| Adaptive Gate — full model (volume + role complexity + distribution) | OUT OF SCOPE | A separate research project on its own; not achievable in this timeline. |
| Progressive expansion, fixed batch sizes, two stopping conditions | IN SCOPE | Buildable in days; central to the upgraded research question. |
| Adaptive batch sizing driven by prior-batch GADS yield | OUT OF SCOPE | Adds a feedback loop that needs its own calibration study. |
| Exhaustion condition + hard-constraint failure-cause logging | IN SCOPE | One governance rule plus one audit-log field; cheap and high-value. |
| GADS core (OPA policy checks, evidence ledger, uncertainty, human-review routing) | IN SCOPE | Existing core of the system; Stage 2 is built on it. |
| Boundary-exploration mechanism (anomaly detection on Stage-1 scores) | OUT OF SCOPE | Requires its own detection model; deferred. |
| Role Assessment Complexity Score (six sub-components) | OUT OF SCOPE | Adds a second full research thread; deferred. |
| Experiment 5 — Stage-1 depth vs recall/cost/stability tradeoff | OPTIONAL | Strongest new idea in the proposal; add only if E1–E4 finish with time to spare. |
| Deployment on live/real applicant data | OUT OF SCOPE | Guardrail — synthetic or anonymized data only (see Section 4). |

# 4. Hard Guardrails

Six non-negotiable constraints. If a future decision conflicts with one of these, the guardrail wins and the decision is dropped, not the reverse.

| Guardrail | What it means in practice |
| --- | --- |
| No live hiring decisions | The system operates only on synthetic or anonymized historical resume data at every stage. It never screens a real applicant for a real vacancy. |
| Single-signal gate, by design | The Adaptive Gate uses the Stage-1 score distribution only. Volume- and role-complexity-based gating are explicitly out of scope; do not add them mid-project. |
| Every decision is auditable | No black-box scores. Every Stage-2 outcome must trace to logged OPA policy checks and an evidence ledger entry. |
| Exhaustion never lowers the bar | If the pool is exhausted and qualified candidates fall short of the target, the system reports the shortfall — plus the dominant failing constraint — rather than relaxing hard requirements to fill a quota. |
| No claim without a logged experiment | Every result stated in the final paper must trace to a reproducible, logged experimental run. Architecture diagrams are not evidence. |
| Scope freeze after Week 3 | No new architectural components after Stage 1 + Gate + Stage 2 are finalized, except the optional Experiment 5 if time allows. |

# 5. Revised 10-Week Timeline

Stage 1 is treated as a new, distinct component that sits before everything the v1.0 plan called “the pipeline.” It is not free — it consumes Weeks 1–2 on its own.

| Week | Tasks | Deliverable / Exit Criterion |
| --- | --- | --- |
| 1–2 | Finalize Stage 1 (extraction, skill normalization, semantic matching) as the preliminary screening funnel. Define target shortlist size K and buffer multiplier for K′. | Stage 1 running end-to-end on synthetic pool; K/K′ fixed and documented. |
| 3 | Implement the Adaptive Gate (score-distribution-only): natural-gap or fixed-percentile selection of K′ from Stage 1's ranked output. | Gate module producing a K′-sized candidate set from any Stage-1 ranking. |
| 4–5 | Build/adapt Stage 2 (GADS): OPA policy checks (hard + soft constraints), evidence ledger, uncertainty computation, human-review routing. | Stage 2 evaluates a candidate set and emits a governed ranking with a full evidence trail. |
| 6 | Implement progressive expansion (fixed batch size, two stopping conditions) and the exhaustion condition with hard-constraint failure-cause logging. | Pipeline correctly expands, stabilizes, or reports exhaustion on test cases designed to trigger each path. |
| 7 | Construct the synthetic evaluation dataset (~100 candidates with known ground-truth qualification labels); instrument logging needed for all experiments. | Dataset finalized; every pipeline run produces the logs each experiment needs. |
| 8 | Run Experiments 1–4 end-to-end on the synthetic dataset. | Raw results for all four core experiments, reproducible from logs. |
| 9 | Analyze E1–E4 results and write them up. If ahead of schedule, run optional Experiment 5 (Stage-1 depth vs. recall/cost/stability). | Analysis complete; E5 results if time allowed. |
| 10 | Assemble the paper draft, figures, and tables; advisor review; incorporate feedback; final submission. | Submission-ready paper and complete audit trail of all runs. |

## 5.1 Contingency Rules

- Behind at the Week 6 checkpoint → drop optional Experiment 5 outright; do not attempt to compress it into Week 9.

- Behind at the Week 8 checkpoint → lock the stopping condition to quantity-threshold only (drop the stability/Jaccard check) and state this simplification explicitly in the paper's limitations section.

- Severely behind (Stage 2 unstable by Week 6) → fall back to a static, non-adaptive K′ (fixed multiplier, no distribution logic) and report this as a design constraint rather than silently dropping the gate.

# 6. Experiments

Four core experiments are mandatory; the fifth is optional and only attempted if Weeks 1–8 finish on schedule. All experiments run on the same synthetic, ground-truth-labeled dataset for comparability.

| Experiment | Question | Metrics |
| --- | --- | --- |
| E1 — Baseline vs. Governed Ranking | How much does Stage 2 (GADS) change the ranking Stage 1 alone would have produced, and why? | Rank correlation (e.g. Kendall's τ) between Stage-1 and Stage-2 rankings; top-K overlap; qualitative review of the largest rank changes against their evidence ledgers. |
| E2 — K′ Buffer Recovery Rate | How many candidates would the final shortlist have lost without the K′ buffer, purely to hard-constraint (P_hard) failures? | Shortlist fill rate at K′ = 1×K (no buffer) vs. 2×K vs. 3×K; number of exhaustion events at each setting. |
| E3 — Gate Precision | How well does the score-distribution-only gate approximate an ideal cutoff, using the synthetic dataset's known ground truth? | Precision/recall of the gate's selected K′ pool against the ground-truth qualified set, at several percentile/gap thresholds. |
| E4 — Shortlist Stability Under Progressive Expansion | How many expansion batches does the pipeline typically need before the shortlist stabilizes, and how stable is it? | Jaccard similarity of the shortlist across consecutive batches; number of batches to convergence; frequency of exhaustion vs. convergence across test runs. |
| E5 — Depth vs. Recall Tradeoff (optional) | How much of the applicant pool actually needs to reach Stage 1's deeper ranking (5–25%) before GADS recovers ~95% of truly qualified candidates? | Recall@K, GADS computation cost, and shortlist stability at each depth setting; identify the point of diminishing returns. |

# 7. Technical Risks

| Risk | Mitigation |
| --- | --- |
| Adaptive Gate systematically excludes a class of qualified candidates | Validate gate precision/recall against ground truth (E3) before relying on it for E1/E2/E4; keep the static-K′ fallback ready. |
| Synthetic dataset is not representative of real resume distributions | Explicitly scope all claims to the synthetic dataset (see Section 8); do not claim real-world generalization. |
| Stage 2 (GADS) build overruns because it is also the project's pre-existing core work | Treat Weeks 4–5 as a hard checkpoint; if OPA policy integration is incomplete, simplify to a smaller rule set rather than delaying Stage 1/Gate integration. |
| Buffer multiplier (K′) is mis-tuned — too small still causes gaps, too large erodes the computational-savings argument | E2 directly measures this; pick the multiplier from E2's results, not a guess, before running E1/E4. |
| Scope creep from further architecture discussion mid-project | Guardrail 6 (scope freeze after Week 3) exists specifically for this; any new idea after Week 3 goes into the future-work section, not the build. |

# 8. What Success Looks Like

## 8.1 Minimum Viable Outcome

- Two-stage pipeline (Stage 1 → Gate → Stage 2) runs end-to-end on the synthetic dataset.

- Experiments E1–E4 completed with results, even if the findings are mixed rather than decisive.

- Full audit trail functioning: every Stage-2 decision traces to logged policy checks and evidence.

- Exhaustion condition and hard-constraint failure-cause logging implemented and demonstrated.

## 8.2 Strong Outcome

- All of the above, plus Experiment 5 completed.

- A clear, quantified operating point stated as a headline finding — e.g. “Stage-1 depth of X% recovers ~95% of qualified candidates while cutting Stage-2 computation by Y%.”

- Gate calibration (from E3) shown to reduce GADS computation by a measurable percentage without a meaningful drop in coverage.

## 8.3 Claims the Paper Will Make

- A two-stage, computationally-governed architecture is feasible and reduces expensive evaluation relative to a single-pass baseline, on the synthetic dataset tested.

- A simple score-distribution gate and a fixed-multiplier buffer measurably improve shortlist completeness and stability over a naive fixed-K design.

## 8.4 Claims the Paper Will NOT Make

- No claim of bias or fairness elimination in hiring — this is a computational governance and evidence-trail study, not a fairness audit.

- No claim of production readiness or deployment validation — synthetic data only, per Guardrail 1.

- No claim that results generalize beyond the synthetic dataset without further, separately-scoped validation.

# 9. Advisor Sign-Off

I have reviewed the scope boundaries, guardrails, and timeline above and agree they define an achievable B.Tech minor-project scope.

Advisor Name: _____________________________

Signature: _____________________________          Date: _______________